## Sheet1
Backlog Item | Owner | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Design Document and Test Case |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design Document Draft | Will | Day 1: 2; Day 2: 0
Test Case Draft |  | Day 1: 2; Day 2: 0
Prototype of Code |  | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Will's Prototype | Will | Day 1: 5; Day 2: 5
Jamie's Prototype | Jamie | Day 1: 5; Day 2: 5
Ben's Prototype | Ben | Day 1: 5; Day 2: 5
Isaac's Prototype | Isaac | Day 1: 5; Day 2: 5
| Estimated Hours | 24 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Working Hours* Until Sprint End | 28 | 26 | 24 | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2
Working Hours = 2 hours per day
INFT 2100 Project Management 702
Scrum Assignment "Game of Life" Sprint 1 Backlog and Sprint 1 Burndown
Owners: James Curnew
William Matheson
Benjamin Allen
Isaac Benoit
Based on: http://www.invisible-city.com/sharon/2008/09/sprint-heartbeat-visual-task-tracking.html